## Sheet1
Activity from Gantt Chat | Start Month | Duration (Months) | Start Month/Year | End Month/Year
Harmonized datasets | 2 | 12 | May 2026 | Apr 2027 | The project will produce Harmonized datasets(start month is May 2026 and end month is Apr 2027)
Cleaned, interoperable dataset of ≥10,000 cases | 3 | 12 | Jun 2026 | May 2027 | The project will produce Cleaned, interoperable dataset of ≥10,000 cases(start month is Jun 2026 and end month is May 2027)
Qualitative narratives structured for AI training | 4 | 10 | Jul 2026 | Apr 2027 | The project will produce Qualitative narratives structured for AI training(start month is Jul 2026 and end month is Apr 2027)
Expanded warehouse with APIs, interoperability validated | 9 | 18 | Dec 2026 | May 2028 | The project will produce Expanded warehouse with APIs, interoperability validated(start month is Dec 2026 and end month is May 2028)
Annotated framework linking local expressions to CMD categories | 5 | 12 | Aug 2026 | Jul 2027 | The project will produce Annotated framework linking local expressions to CMD categories(start month is Aug 2026 and end month is Jul 2027)
Mobile and Web Applications | 14 | 18 | May 2027 | Oct 2028 | The project will produce Mobile and Web Applications(start month is May 2027 and end month is Oct 2028)
Usability dataset (AI summaries, screening scale data, session logs) | 12 | 20 | Mar 2027 | Oct 2028 | The project will produce Usability dataset (AI summaries, screening scale data, session logs)(start month is Mar 2027 and end month is Oct 2028)
Interactive Multimorbidity dashboard online | 18 | 22 | Sept 2027 | Jun 2029 | The project will produce Interactive Multimorbidity dashboard online(start month is Sept 2027 and end month is Jun 2029)
Formulas:
Start Month/Year = TEXT(EDATE(DATE(2026,4,1),[Start Month]-1),"mmm yyyy")
End Month/Year = TEXT(EDATE(DATE(2026,4,1),[Start Month]+[Duration (Months)]-2),"mmm yyyy")